Department of Computer Science & Information Technology

## Standard Operating Procedures (SOP) for Final Year Projects

### 1. Objective & Scope

This SOP defines the processes, milestones, and compliance requirements for the successful completion of the Final Year Project. The project structure follows a 4-month (tentative) timeline divided into specific phases: Topic Selection, Reproducibility, Enhancement, and Finalization.

2. Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Student | Execute tasks per timeline, maintain weekly reports, achieve reproducibility metrics, implement enhancements. |
| Project Guide | Approve topic/paper, verify reproduction results, sign weekly reports, provide technical guidance. |
| Project Review Committee (PRC) | Monitor progress, enforce SOP compliance, conduct assessments, approve/reject project at any stage. |

### 3. Project Phases & Mandatory Actions

#### Month 1: Topic & Paper Selection

- Week 1-2: Select one paper from approved domains (Theory, Systems, AI/ML, or Software Engineering). Use only recommended data sources (e.g., Hugging Face, PhysioNet, Microsoft Research, Google Datasets).

NOTE: Kaggle Datasets are not accepted.

- Week 3-4 – Critical Red Flag Rule:
You must download and run the original code of the selected paper.

  - Annotate paper section-by-section. Identify: inputs, outputs, key equations, hyperparameters.

  - Identify algorithms/framework/architecture/flowchart(s).

  - If the code runs successfully → proceed.

  - If the original code does NOT run → abandon the paper immediately and select a new one.

  - Failure to comply will result in automatic project rejection by PRC.

#### Month 2: Reproducibility

- Goal: Reproduce the core results from the paper.

- Acceptable tolerance:

  - ML/AI tasks: ±5–10% of reported metric.

  - Numerical simulations: ±1–2%.

- If your numbers differ beyond tolerance: You must document the exact reason (e.g., different hardware, library versions, dataset split). Otherwise, reproduction is considered failed.

- Completion definition: "Reproduction complete" = numbers within range OR documented deviation with justification.

#### Month 3: Enhancement Planning & Execution

Choose exactly one tier based on your progress and guide’s approval:

| Tier | Type | Example | Condition |
| --- | --- | --- | --- |
| 1 (Standard) | Hyperparameter tuning / Augmentation | Grid search, data augmentation | Original runs well |
| 2 (Ambitious) | Module replacement | Replace slow module with faster alternative | Guide approval required |
| 3 (Risky) | Novel combination / new dataset | Apply model to new domain | Only if original ran early (by Week 4) |

- Enhancements must be executed and working by end of Month 3.

#### Month 4: Finalization & Documentation

- Complete code repository (with README, requirements, run instructions).

- Final report including: original paper results, your reproducibility results, enhancement details, and performance comparison.

- Prepare presentation slides for final assessment.

### 4. Weekly Status Report – Mandatory Submission

⚠️ Critical Rule: The weekly report must be submitted only after discussing with your project guide. The guide’s signature (physical or digital) is mandatory.

- Format (to be submitted every Saturday by 2:00 PM)

- Late submission (without prior approval) → deduction of 5% from final grade per occurrence.

- Three consecutive missing reports → automatic project rejection.

### 5. Compliance & Rejection Authority of Project Review Committee (PRC)

PRC Members:

| PRC – Team I | PRC – Team II |
| --- | --- |
| Dr. Sk Khaja Shareef | Dr. K Venkateswara Rao |
| Dr. Jagan Mohan Reddy | Dr. B Sivaiah |
| Dr. Prasanna Lakshmi | Dr. M Gayatri |
| Mr. P Krishnanjaneyulu | Mr. B Dwarakanath |

The Project Review Committee (PRC) has the absolute authority to reject the project at any time if any of the following violations occur:

| Violation | Consequence |
| --- | --- |
| Original code not run / not reproducible by Week 4 | Immediate rejection |
| Weekly reports submitted without guide’s discussion or signature | Rejection after 2 warnings |
| Falsification of reproduction metrics | Immediate rejection + academic misconduct |
| Enhancement tier chosen without justification or guide approval | Rejection during Month 3 review |
| Use of unapproved data sources or change of research domain | Rejection at any stage |
| Missing 3 weekly reports (consecutive or total) | Automatic rejection |

NOTE: A rejected project is not eligible for final assessment. No re-submission is allowed.

6. Recommended Grade Breakdown (for assessment alignment)

| Component | Weight |
| --- | --- |
| Weekly report compliance & guide feedback | 20% |
| Reproduction accuracy (± tolerance) | 30% |
| Enhancement (quality & documentation) | 25% |
| Final report & presentation | 25% |

### 7. Implementation aspects

- Students must develop either full-stack app or bundle into PyPI/node.js/VS-code extension

- Every module/code file must be available in GitHub. Every student must contribute to the project, failure to comply will result in deduction of grade.

- Students must invite their supervisor to track the project activity like git commits or by another means.

### 8. Summary Checklist for Students

- Paper selected from approved domains

- Original code runs by end of Week 4 (switch if not)

- Reproduction completed within tolerance or documented

- Enhancement tier chosen and approved

- Weekly report discussed with guide and signed each week

- Final code, report, and presentation submitted by Month 4 end

9. Useful resources

- https://arxiv.org  (paper must be selected from this portal only)

- https://mermaid.live (workflow diagrams)

- https://github.com (Code repo)

- https://www.overleaf.com (documentation)

  - https://www.overleaf.com/read/mntmbckmngyg#dca61d (our template)

- Datasets

  - https://physionet.org/

  - https://www.microsoft.com/en-us/research/tools/

  - https://huggingface.co/datasets

  - https://research.google/resources/datasets/

  - https://www.cancerimagingarchive.net/

  - https://openneuro.org/

Approved by:
Project Review Committee (PRC)
Effective Date:

Department of Computer Science & Information Technology

Weekly Status Report

Date:

Project Title:

Week (X of 16):

Status: pending / progressing / on track

What I planned to do:

-

-

-

What I actually did:

-

-

-

Reproduction metrics (if applicable):

- Paper's reported: _______

- My reproducibility: _______

- Difference: ______%

Blockers (if any):

-

-

Next week's plan:

Supervisor Signature